## Start
Orange-Senqu River Commission
Monitoring and Budget Planning System
M&E Overview
Budget Planning Gantt Chart
Funding Overview
About

## Overview
Orange-Senqu River Commission - Overview
Vision | Sustainable management and development of the Orange-Senqu River Basin
Theme
| Component 1 | [5 empty] | Component 2 | [7 empty] | Component 3
| Governance | [5 empty] | IWRM/TWM | [7 empty] | Capacity Development
Outcome | ORASECOM is functional to service its member states and stakeholders in line with the Orange-Senqu Watercourse Agreement | [5 empty] | Integrated water resources management and development is implemented in the Orange-Senqu River Basin | [7 empty] | Capacities of ORASECOM relevant institutional frameworks, organisations and staff stregthened
Line of | 1.1 |  | 1.2 |  | 1.3 |  | 2.1 |  | 2.2 |  | 2.3 |  | 2.4 |  | 3.1 |  | 3.2 |  | 3.3
Action | Management |  | Participation |  | Communication |  | Assessments |  | Planning |  | Implementaton |  | Monitoring |  | Institutional |  | Organisational |  | Individual
Objective | The Commission and all its structures are fully functional |  | The relevant stakeholders are engaged to support the implementation of the ORASECOM agreement |  | Stakeholders are timely informed about developments in the Orange-Senqu River Basin |  | Adequate assessments are undertaken to develop strategies and plans |  | Concrete overall stategies and plans are developed to implement interventions at basin-wide and national levels |  | Specific interventions are implemented as devised in the IWRM strategy and/or implementation plans |  | Adequate (real-time) monitoring and evaluation system in place to avoid disasters and ensure effective implementation of the IWRM plan(s) |  | The institutional framework is in place to implement the ORASECOM agreement |  | Lessons Learned and best practice from other RBOs are integrated into the ORASECOM organisation |  | Human resources capacity is improved to implement the ORASECOM Agreement
Outputs | 1.1.01 | b | 1.2.01 | b | 1.3.01 | a | 2.1.01 | b | 2.2.01 |  | 2.3.01 | b | 2.4.01 | b | 3.1.01 | a | 3.2.01 | b | 3.3.01 | a
| 1.3.1 Secretariat operations |  | 1.4 Intersectoral Committees |  | 4.1 ORASECOM Website |  | 3.3.2 Updated and extended hydrological data set |  | 5.5 Decision support guidelines and knowledge management system for ground water drought management (SADC Water Division) |  | 5.1 Demonstration project on water conservation and quality control in the Irrigation sector |  | 3.1.2 GIS based information management system |  | 1.1 Review of Legal issues |  | 2.3.1 RBO exchange programme |  | 2.2.1 Needs Assessment and Capacity Building Programme
| ORASECOM |  | UNDPGEF |  | GTZ |  | GTZ |  | SADC |  | UNDPGEF |  | UNDPGEF |  | EU |  | GTZ |  | EU-FGEF
| 1.1.02 | b | 1.2.02 | a | 1.3.02 | a | 2.1.02 | b | 2.2.02 | b | 2.3.02 | b | 2.4.02 | b | 3.1.02 | b | 3.2.02 |  | 3.3.02 | a
| 1.3.2 Office and Facilities |  | 1.5 Stakeholder Roadmap |  | 3.1.1 Orange-Senqu River Basin Awareness Kit |  | 4.4 Revised TDA |  | 5.9.5 Integrated Water Resources Quality Management Plan |  | 5.7 Demonstration project on Environmental flows in Fish River and the Orange-Senqu Mouth |  | 3.3.1 Data acquisition and display system |  | 1.2.1 Review of ORASECOM roles, responsibilities, mandates and operational procedures |  | x |  | 2.2.2 Training course on International Water Law
| GTZ |  | EU |  | GTZ |  | UNDPGEF |  | EU-GTZ |  | UNDPGEF |  | GTZ |  | EU |  | 0 |  | EU-FGEF
| 1.1.03 | b | 1.2.03 | b | 1.3.03 | b | 2.1.03 | b | 2.2.03 | a | 2.3.03 | b | 2.4.03 | b | 3.1.03 | a | 3.2.03 |  | 3.3.03 | b
| 1.3.3 Procedure and Systems |  | 1.8 Basin-wide Stakeholder Forum |  | 4.1 Awarenes Programme for Political decision-makers |  | 5.1 Best practice on water demand management in the Irrigation Sector |  | 6.1.1. Guidelines for water and benefit sharing |  | 5.9.6 Demonstration project on community-led rangeland management |  | Joint Basin Survey on Water Resources Quality |  | 6.1.2 Review of basin-wide institutional issues |  | x |  | 2.2.3 Training course on Integrated Orange-Senqu Basin Model
| GTZ |  | GTZ-UNDPGEF |  | GTZ |  | GTZ-UNDPGEF |  | EU |  | UNDPGEF |  | MS, GTZ, EU, UNDP-GEF, LHDA |  | EU |  | 0 |  | GTZ
| 1.1.04 | b | 1.2.04 | B | 1.3.04 | a | 2.1.04 | b | 2.2.04 | b | 2.3.04 | d | 2.4.04 | d | 3.1.04 | b | 3.2.04 |  | 3.3.04 | a
| 1.3.4 Regular and Extraordinary meetings |  | 1.8 National Stakeholder Forums |  | 4.1 Awareness materials for portfolio committees |  | 5.2.1 Impact study on climate change |  | 6.1.3 Strategic Action Plan (SAP) |  | Establishment of a Fund for Catchment Conservation |  | Aquatic Ecosystem Health Monitoring |  | 1.2.2 Review of international best practices for transboundary water management |  | x |  | 2.2.4 Training course on SADC Treaties and UN Conventions
| GTZ |  | Member states+EU+UNDPGEF |  | EU |  | GTZ |  | UNDPGEF |  | 0 |  | EU |  | EU |  | 0 |  | EU
| 1.1.05 | b | 1.2.05 | B | 1.3.05 | b | 2.1.05 | b | 2.2.05 | b | 2.3.05 | d | 2.4.05 | d | 3.1.05 | b | 3.2.05 |  | 3.3.05 | a
| ICPs Coordination |  | 1.8 Sub-basin Councils |  | 4.2 Print and broadcast materials |  | 5.3 Assessment of the contribution of Groundwater to basin flow |  | 2.1.2 National Action Plans (NAPs) for IWRM implementation |  | Implementation of an ORASECOM capacity building programme |  | Extension of ground water monitoring to remote areas in the Molopo-Nossob Sub Basin and capturing of natural changes |  | 1.9 Transboundary EIA Procedures |  | x |  | 2.2.4 Training course on Negotiation skills and conflict management
| 0 |  | UNDPGEF |  | EU-UNDPGEF |  | GTZ |  | UNDPGEF |  | 0 |  | 0 |  | UNDPGEF |  | 0 |  | EU
| 1.1.06 | b | 1.2.06 | b | 1.3.06 | b | 2.1.06 | b | 2.2.06 | b | 2.3.06 | d | 2.4.06 | d | 3.1.06 | b | 3.2.06 |  | 3.3.06 | b
| 1.6 M&E System |  | Strategic Partnerships (ICPDR, Sasol, etc) |  | 4.2 Awarenes materials on IWRM |  | 5.4 Inventory of transboundary aquifers and vulnerability map (ISARM/UNESCO) |  | 3.1.4 An Integrated Orange-Senqu River Basin Model accessible to all basin states |  | Establishment of an integrated Molopo-Nossob Sub-Basin Groundwater Database |  | Monitoring of changes in ongoing groundwater table lowering |  | 2.1.1 Agreement and financial arrangements for NAP development |  | x |  | 2.2.5 Training course on Transboundary Water Resources Management
| ORASECOM |  | ICPDR, Sasol, etc |  | EU-UNDPGEF |  | 0 |  | GTZ |  | 0 |  | 0 |  | UNDPGEF |  | 0 |  | UNDPGEF
| 1.1.07 | a | 1.2.07 |  | 1.3.07 | b | 2.1.07 | a | 2.2.07 | d | 2.3.07 | d | 2.4.07 |  | 3.1.07 |  | 3.2.07 |  | 3.3.07 | b
| 1.7 Funding mechanisms |  | x |  | 4.2.1 Regional and International Conferences |  | 5.6 Review of water resources development potential of the Molopo-Nossob |  | 6.1 Basin-wide IWRM Plan |  | Lesotho: Irrigation of sport fields, the golf course and suitable food crops in Maseru with treated wastewater |  | x |  | x |  | x |  | Scholarship Programme
| FGEF |  | 0 |  | EU-UNDPGEF |  | FGEF |  | GTZ |  | 0 |  | 0 |  | 0 |  | 0 |  | ICPDR
| 1.1.08 | d | 1.2.08 |  | 1.3.08 | b | 2.1.08 | b | 2.2.08 | d | 2.3.08 | d | 2.4.08 |  | 3.1.08 |  | 3.2.08 |  | 3.3.08 | d | Completed (deliverable
| Map/inventory of activities in the basin |  | x |  | 4.3 "State of the Environment report" |  | 5.7 Assessment of Environmental Flow Requirements |  | 6.1.5 Donor Conference on the basin wide IWRM Plan |  | Namibia: Irrigation of sport fields and suitable food crops in larger Namibian towns with treated waste water |  | x |  | x |  | x |  | Botswana: Awareness campaign to promote indirect potable water reuse and irrigation of food crops with treated sewage effluent |  | On track
Implementation Problem
| 0 |  | 0 |  | EU |  | GTZ-UNDPGEF |  | GTZ-UNDPGEF |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Planned
| 1.1.09 | d | 1.2.09 |  | 1.3.09 | a | 2.1.09 | a | 2.2.09 | d | 2.3.09 | d | 2.4.09 |  | 3.1.09 |  | 3.2.09 |  | 3.3.09
| Human Resources Management System |  | x |  | 3.1.3 "Fitness for Use" Map |  | 5.8 Assessment of development and use of marginal waters |  | South Africa: Dual reticulation system guidelines for Gauteng (promotion of marginal water use) |  | Protection, rehabilitation and conservation of the Orange-Senqu sources (Sponges) |  | x |  | x |  | x |  | x
| 0 |  | 0 |  | EU |  | FGEF |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 1.1.10 | d | 1.2.10 |  | 1.3.10 | d | 2.1.10 | b | 2.2.10 | d | 2.3.10 |  | 2.4.10 |  | 3.1.10 |  | 3.2.10 |  | 3.3.10
| Financial Management System |  | x |  | Communication Strategy |  | 5.9.1 Assessment of persistent organic pollutants contamination |  | Transboundary: Institutional, Policy, Legislative and Guidelines Review of the use marginal waters |  | x |  | x |  | x |  | x |  | x
| 0 |  | 0 |  | EU |  | UNDPGEF |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 1.1.11 |  | 1.2.11 |  | 1.3.11 |  | 2.1.11 | b | 2.2.11 | d | 2.3.11 |  | 2.4.11 |  | 3.1.11 |  | 3.2.11 |  | 3.3.11
| #N/A |  | #N/A |  | #N/A |  | 5.9.2 Scoping study on urban water pollution |  | Transboundary: Guidelines for marginal water use for the industrial sector |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
| #N/A |  | #N/A |  | #N/A |  | EU |  | 0 |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
| 1.1.12 |  | 1.2.12 |  | 1.3.12 |  | 2.1.12 | b | 2.2.12 |  | 2.3.12 |  | 2.4.12 |  | 3.1.12 |  | 3.2.12 |  | 3.3.12
| #N/A |  | #N/A |  | #N/A |  | 5.9.3 Impact review of artisanal mining |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
| #N/A |  | #N/A |  | #N/A |  | UNDPGEF |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
| 1.1.13 |  | 1.2.13 |  | 1.3.13 |  | 2.1.13 | b | 2.2.13 |  | 2.3.13 |  | 2.4.13 |  | 3.1.13 |  | 3.2.13 |  | 3.3.13
| #N/A |  | #N/A |  | #N/A |  | 5.9.4 Status of the deterioration and protection of Orange-Senqu sources (sponges) |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
| #N/A |  | #N/A |  | #N/A |  | FGEF |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
| 1.1.14 |  | 1.2.14 |  | 1.3.14 |  | 2.1.14 | b | 2.2.14 |  | 2.3.14 |  | 2.4.14 |  | 3.1.14 |  | 3.2.14 |  | 3.3.14
| #N/A |  | #N/A |  | #N/A |  | Investigation of the continuation of the Nossob sandstone aquifer from Namibia into Botswana |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
| #N/A |  | #N/A |  | #N/A |  | x |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
| 1.1.15 |  | 1.2.15 |  | 1.3.15 |  | 2.1.15 | b | 2.2.15 |  | 2.3.15 |  | 2.4.15 |  | 3.1.15 |  | 3.2.15 |  | 3.3.15
| #N/A |  | #N/A |  | #N/A |  | Employment of more approaches to determine groundwater recharge |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
| #N/A |  | #N/A |  | #N/A |  | x |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
Legends
A
Completed (deliverable produced)
B
On track
C
Implementation Problem /delayed
D
Planned
Initial
ICP
Theme 1. Institutional and Organisational Strengthening
Theme 4. Enhancing ORASECOM Communication and Awareness Building
Theme 5. Specific Transboundary Projects and Studies
Theme 6. Promotion of Conservation and Environmental Strategies and Policies
Theme 3. Development of Shared Information System
Theme 2. Specific Capacity Building on Shared Watercourses Management

## Programme
Orange-Senqu River Commission - Overview
Vision | Sustainable management and development of the Orange-Senqu River Basin
Theme
| Component 1 |  |  | Component 2 |  |  |  | Component 3
| Governance |  |  | IWRM/TWM |  |  |  | Capacity Development
Outcome | ORASECOM is functional to service its member states and stakeholders in line with the Orange-Senqu Watercourse Agreement |  |  | Integrated water resources management and development is implemented in the Orange-Senqu River Basin |  |  |  | Capacities of ORASECOM relevant institutional frameworks, organisations and staff stregthened
Line of | 1.1 | 1.2 | 1.3 | 2.1 | 2.2 | 2.3 | 2.4 | 3.1 | 3.2 | 3.3
Action | Management | Participation | Communication | Assessments | Planning | Implementaton | Monitoring | Institutional | Organisational | Individual
Objective | The Commission and all its structures are fully functional | The relevant stakeholders are engaged to support the implementation of the ORASECOM agreement | Stakeholders are timely informed about developments in the Orange-Senqu River Basin | Adequate assessments are undertaken to develop strategies and plans | Concrete overall stategies and plans are developed to implement interventions at basin-wide and national levels | Specific interventions are implemented as devised in the IWRM strategy and/or implementation plans | Adequate (real-time) monitoring and evaluation system in place to avoid disasters and ensure effective implementation of the IWRM plan(s) | The institutional framework is in place to implement the ORASECOM agreement | Lessons Learned and best practice from other RBOs are integrated into the ORASECOM organisation | Human resources capacity is improved to implement the ORASECOM Agreement
Theme 1. Institutional and Organisational Strengthening
Theme 4. Enhancing ORASECOM Communication and Awareness Building
Theme 5. Specific Transboundary Projects and Studies
Theme 6. Promotion of Conservation and Environmental Strategies and Policies
Theme 3. Development of Shared Information System
Theme 2. Specific Capacity Building on Shared Watercourses Management

## Budget Planning
Management | ORASECOM Budget Plannig Gantt Chart | [9 empty] | 2008 |  |  |  | 2009 |  |  |  | 2010 |  |  |  | 2011 |  |  |  | 2012
| Output# | Seq | Output | Sub-Output | ICP | Funding Status | Currency | Amount | ZAR | 2007-Q4 | 2008-Q1 | 2008-Q2 | 2008-Q3 | 2008-Q4 | 2009-Q1 | 2009-Q2 | 2009-Q3 | 2009-Q4 | 2010-Q1 | 2010-Q2 | 2010-Q3 | 2010-Q4 | 2011-Q1 | 2011-Q2 | 2011-Q3 | 2011-Q4 | 2012-Q1 | 2012-Q2 | 2012-Q3 | 2012-Q4 | Progress
| 1.1.01 | 0 | 1.3.1 Secretariat operations |  | ORASECOM
| 1.1.01.1 |  |  | 1.3.1 Secretariat operations | ORASECOM | 2 | ZAR | 10000000 |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | ongoing
| 1.1.02 | 0 | 1.3.2 Office and Facilities |  | GTZ
| 1.1.02.1 |  |  | 1.3.2 Office Establishment and Facilities | GTZ | 1 | EUR | 10000 |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [6 empty] | Ongoing.
| 1.1.03 | 0 | 1.3.3 Procedure and Systems |  | GTZ
| 1.1.03.1 |  |  | 1.3.3 Procedure and Systems | GTZ | 1 | EUR | 15000 |  |  |  | x | x | x | x | x | x | x | x | [11 empty] | 50% complete.
| 1.1.04 | 0 | 1.3.4 Regular and Extraordinary meetings |  | GTZ
| 1.1.04.1 |  |  | 1.3.4 Regular and Extraordinary meetings | GTZ | 1 | EUR | 75000 |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | [6 empty] | Ongoing.
| 1.1.05 | 0 | ICPs Coordination
| 1.1.05.1 |  |  | ICPs Meetings
| 1.1.05.2 |  |  | Programme Strategy Committee Meetings
| 1.1.06 | 0 | 1.6 M&E System |  | ORASECOM
| 1.1.06.1 |  |  | 1.6.1 Updating of a global Gantt Chart | ORASECOM | 1 | [5 empty] | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | To be updated for every Council meeting
| 1.1.07 | 0 | 1.7 Funding mechanisms |  | FGEF
| 1.1.07.1 |  |  | 1.7.1 Mechanism for funding catchment conservation | FGEF | 1 | EUR | 71800 |  |  |  |  | x | x | x | x | [14 empty] | 100% complete.
| 1.1.08 | 0 | Map/inventory of activities in the basin
| 1.1.09 | 0 | Human Resources Management System
| 1.1.10 | 0 | Financial Management System
Stakeholder | 1.2.01 | 0 | 1.4 Intersectoral Committees |  | UNDPGEF
| 1.2.01.1 |  |  | 1.4.1 Establishment and support to intersectoral committees (Timing: following 1.2.1) | UNDPGEF | 2 | USD | 150000 | [11 empty] | x | x | x | x | x | x | x | x | x | x | x | To commence in Q2, 2010.
| 1.2.02 | 0 | 1.5 Stakeholder Roadmap |  | EU
| 1.2.02.1 |  |  | 1.5.1 Review of the ORASECOM Stakeholder Roadmap for its pros/cons to propose a structure for the establishment of a stakeholder forum in each basin state designed to bring primary and secondary stakeholders together (EU4.2) (linked to 1.8.1) | EU | 1 | EUR | 125500 | [6 empty] | x | x | x | x | x | [11 empty] | 100% complete.
| 1.2.03 | 0 | 1.8 Basin-wide Stakeholder Forum |  | GTZ-UNDPGEF
| 1.2.03.1 |  |  | 1.8.1 The establishment of and support to a basin wide forum and a national stakeholder forum in each basin state (Timing: following 1.5.1) | GTZ | 1 | EUR | 50000 | [11 empty] | x | x | x | x | x | x | x | x | x |  |  | To be started in Q2, 2010.
| 1.2.03.2 |  |  | 1.8.1 The establishment of and support to a basin wide forum (Timing: following 1.5.1) | UNDPGEF |  | USD | 50000 | [11 empty] | X | X | X | X | X | X | X | X | X
| 1.2.04 | 0 | 1.8 National Stakeholder Forums |  | Member states+EU+UNDPGEF
| 1.2.04.1 |  |  | 1.8.1 The establishment and support of national stakeholder forums | Member states | 2 | [13 empty] | x | x | x | x | x | x | x | x | x |  |  | To be started in Q2, 2010.
| 1.2.04.2 |  |  | 1.8.1 Mobilisation of stakeholder participation in ORASECOM | EU |  | EUR | 15000 | [11 empty] | X | X | X | X | X
| 1.2.04.3 |  |  | 1.8.1 The establishment and support to national stakeholder forums | UNDPGEF |  | USD | 50000 | [11 empty] | X | X | X | X | X | X | X | X | X
| 1.2.05 | 0 | 1.8 Sub-basin Councils |  | UNDPGEF
| 1.2.05.1 |  |  | 1.8.2 Supporting of the establishment of sub-basin Councils | UNDPGEF | 2 | USD | 300000 | [11 empty] | x | x | x | x | x | x | x | x | x |  |  | To be started in Q2, 2010.
| 1.2.06 | 0 | Strategic Partnerships (ICPDR, Sasol, etc) |  | ICPDR, Sasol, etc | 2
| 1.2.07 | 0 | x
| 1.2.08 | 0 | x
| 1.2.09 | 0 | x
| 1.2.10 | 0 | x
Communication | 1.3.01 | 0 | 4.1 ORASECOM Website |  | GTZ
| 1.3.01.1 |  |  | 4.1.1 Establishing ORASECOM Website | GTZ | 1 | EUR | 15000 | [22 empty] | 100% complete.
| 1.3.01.2 |  |  | Enhancement and/or establishment of web-based information management and sharing systems | ICPDR | 1 | EUR | 2000
| 1.3.02 | 0 | 3.1.1 Orange-Senqu River Basin Awareness Kit |  | GTZ
| 1.3.02.1 |  |  | 3.1.1 Development of the Orange-Senqu River Basin Awareness Kit (Web- and CD-based) | GTZ | 1 | EUR | 400000 |  |  |  |  | x | x | x | x | x | [13 empty] | 100% complete.
| 1.3.03 | 0 | 4.1 Awarenes Programme for Political decision-makers |  | GTZ
| 1.3.03.1 |  |  | 4.1.2 Development and presentation of awareness programme for political decision makers (incl.African diplomats in key centers) | GTZ | 1 | EUR | 50000 | [9 empty] | x | x | x | [10 empty] | being done under GTZ phase II project
| 1.3.04 | 0 | 4.1 Awareness materials for portfolio committees |  | EU
| 1.3.04.1 |  |  | 4.1.3 Development and presentation of awareness materials for portfolio committees in all member countries | EU | 1 | EUR | 83000 | [6 empty] | x | x | x | x | [12 empty] | 100% complete.
| 1.3.05 | 0 | 4.2 Print and broadcast materials |  | EU-UNDPGEF
| 1.3.05.1 |  |  | 4.2.2 Production and dissemination of print and broadcast materials: UNDP/GEF:Coffee table books) | UNDPGEF | 2 | USD | 300000 | [7 empty] | x | x | x | x | x | x | x | x | x | x | [5 empty] | 50% complete.
| 1.3.05.2 |  |  | 4.2.2 Production and dissemination of print and broadcast materials - EU: Fitness for use maps&pamphlets, aquatic ecosystem health maps&pamphlets | EU | 1 | EUR | 145000 | [7 empty] | x | x | x | x | x | x | x | x | x | x | [5 empty] | 50% complete.
| 1.3.06 | 0 | 4.2 Awarenes materials on IWRM |  | EU-UNDPGEF
| 1.3.06.1 |  | 4.2 Raising awareness among general public | 4.2.3 Preparation, printing and dissemination of awareness materials on IWRM: EU:WR availability, per sector water use, water demand projections | EU | 1 | EUR | 252000 | [7 empty] | x | x | x | x | x | x | x | x | x | [6 empty] | 50% complete.
| 1.3.06.2 |  | 4.2 Raising awareness among general public | 4.2.3 Preparation, printing and dissemination of awareness materials on IWRM: UNDP/GEF: materials for environ education, awareness, eco-tourism and social marketing, etc.) | UNDPGEF | 2 | USD | 200000 | [7 empty] | x | x | x | x | x | x | x | x | x | [6 empty] | 50% complete.
| 1.3.07 | 0 | 4.2.1 Regional and International Conferences |  | EU-UNDPGEF
| 1.3.07.1 |  | 4.2 Raising awareness among general public | 4.2.1 Support to annual ORASECOM event | EU | 1 | EUR | 126000 | [22 empty] | 50% complete.
| 1.3.07.2 |  |  | 2.3.2 GEF Biennial International Waters Conference | UNDPGEF | 2 | USD | 20000 | [8 empty] | x | [13 empty] | 100% complete
| 1.3.08 | 0 | 4.3 "State of the Environment report" |  | EU
| 1.3.08.1 |  | 4.3 Preparation and publication of the "State of the Environment report" | 4.3.1 Development and agreement on methods and sites for assessing transboundary aquatic ecosystem health, and piloting of assessment tool towards development of baseline | EU | 1 | EUR | 330000 | [7 empty] | x | x | x | x | x | x | x | x | x | [6 empty] | 60% complete.
| 1.3.08.1 |  | 4.3 Preparation and publication of the "State of the Environment report" | 4.3.2 Collation and coordination of the production of the state of the environment report for the Orange-Senqu. | x | 3 | x |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| 1.3.09 | 0 | 3.1.3 "Fitness for Use" Map |  | EU
| 1.3.09.1 |  |  | 3.1.3 Creation of the "fitness for use" display system | EU | 1 | EUR | 64300 | [8 empty] | x | x | x | [11 empty] | 100% complete.
| 1.3.09.2 |  |  | 3.2.2 Review and development of water quality database | EU | 1 | EUR | 96000 |  |  |  |  | x | x | x | x | x | x | x | [11 empty] | 100% complete.
| 1.3.10 | 0 | Communication Strategy |  | EU | [8 empty] | x | x | x | x | x | x | x
| 1.3.10.1 |  |  | Calendar
| 1.3.10.2 |  |  | Communications Plan
Assessments | 2.1.01 | 0 | 3.3.2 Updated and extended hydrological data set |  | GTZ
| 2.1.01.1 |  |  | 3.3.2 Updating and extension of Orange-Senqu River Hydrology | GTZ | 1 | EUR | 330167 | [8 empty] | x | x | x | x | x | x | [8 empty] | 15% complete
| 2.1.02 | 0 | 4.4 Revised TDA |  | UNDPGEF
| 2.1.02.1 |  | 4.4 TDA revised, updated and disseminated |  | UNDPGEF | 2 | USD | 230000 |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| 2.1.03 | 0 | 5.1 Best practice on water demand management in the Irrigation Sector |  | GTZ-UNDPGEF
| 2.1.03.1 |  |  | 5.1.2 An Assessment of the potential for Water Demand Management in the irrigation sector of the Orange-Senqu River Basin (complementary sites) (Outcomes contributing to 3.1.4) | GTZ | 1 | EUR | 279967 | [9 empty] | x | x | x | x | x | x | [7 empty] | 20% complete
| 2.1.03.2 |  |  | 5.2.2 Water demand forecasting taking into account climate change (part of TDA gap filling) | UNDPGEF | 2 | USD | 200000 | [11 empty] | x | x | x | x | x | [6 empty] | To commence in Q2, 2010.
| 2.1.04 | 0 | 5.2.1 Impact study on climate change |  | GTZ
| 2.1.04.1 |  |  | 5.2.1 Assessment of the impact of climate change on the Orange-Senqu River Basin | GTZ | 1 | EUR | 179717 | [9 empty] | x | x | x | x | x | x | [7 empty] | 15% complete
| 2.1.05 | 0 | 5.3 Assessment of the contribution of Groundwater to basin flow |  | GTZ
| 2.1.05.1 |  |  | 5.3.1 Determination of catchment boundaries | GTZ | 1 | EUR | 50000 | [9 empty] | x | x | x | x | x | x | x | x | [5 empty] | Work commenced in Q4, 2009
| 2.1.06 | 0 | 5.4 Inventory of transboundary aquifers and vulnerability map (ISARM/UNESCO)
| 2.1.06.1 |  |  | 5.4 Inventory and study of transboundary aquifers and vulnerability map (ISARM/UNESCO) |  | 3 | [24 empty] | SADC and UNESCO intiatives.
| 2.1.07 | 0 | 5.6 Review of water resources development potential of the Molopo-Nossob |  | FGEF
| 2.1.07.1 |  |  | 5.6.1 Feasibility of water resources development in the Molopo-Nossob | FGEF | 1 | EUR | 155400 |  | x | x | x | x | x | [16 empty] | 100% Completed.
| 2.1.07.2 |  |  | 3.2.1 Review of databases on groundwater in Molopo-Nossob | FGEF | 1 | EUR | 50000 |  |  |  |  | x | x | x | x | [14 empty] | 100% completed as originally scheduled.
| 2.1.07.3 |  |  | 5.6.2 Detailed ground water review of the Molopo basin (South Africa, Botswana and Namibi) for rural communities | FGEF | 1 | EUR | 137700 |  |  |  |  | x | x | x | x | [14 empty] | 100% complete.
| 2.1.08 | 0 | 5.7 Assessment of Environmental Flow Requirements |  | GTZ-UNDPGEF
| 2.1.08.1 |  |  | 5.7.2 Assessment of Environmental Requirements (in other basin hotspots and development of harmonised methodologies) | GTZ | 1 | EUR | 788632 | [8 empty] | x | x | x | x | x | x | x | [7 empty] | 20% complete
| 2.1.08.2 |  |  | 5.7.3 Strategic environmental assessment of the Orange-Senqu River Mouth | x | 3 | [12 empty] | x | x | x | x | x | x | [6 empty] | No longer supported by EU. Components to be dealt with under UNDP-GEF Estuarine Flows.
| 2.1.08.3 |  |  | 5.7.1 Assessment of Environmental Water Requirements of the Estuary | UNDPGEF | 2 | USD | 1150000 | [11 empty] | x | x | x | x | x | x | x |  |  |  |  | To commence in Q2, 2010.
| 2.1.09 | 0 | 5.8 Assessment of development and use of marginal waters |  | FGEF
| 2.1.09.1 |  |  | 5.8.1 Assessment of the potential for the increased use of "marginal" waters in the Orange-Senqu River Basin | FGEF | 1 | EUR | 80400 |  |  |  |  | x | x | x | x | [14 empty] | 100% complete.
| 2.1.10 | 0 | 5.9.1 Assessment of persistent organic pollutants contamination |  | UNDPGEF
| 2.1.10.1 |  |  | 5.9.1 Assessment of persistent organic pollutants contamination in the Orange-Senqu | UNDPGEF | 2 | USD | 210000 | [11 empty] | x | x | x | x | x | x | x | x |  |  |  | To commence in Q2, 2010.
| 2.1.11 | 0 | 5.9.2 Scoping study on urban water pollution |  | EU
| 2.1.11.1 |  |  | 5.9.2 Scoping study on transboundary nature of urban water pollution | EU | 1 | EUR | 82000 | [11 empty] | x | x | [9 empty] | To be implemented in Q3 of 2010.
| 2.1.12 | 0 | 5.9.3 Impact review of artisanal mining |  | UNDPGEF
| 2.1.12.1 |  |  | 5.9.3 Review of impact of artisanal mining on the middle and lower Orange-Senqu | UNDPGEF | 2 | USD | 60000 | [11 empty] | x | x | x | [8 empty] | To commence in Q2, 2010.
| 2.1.13 | 0 | 5.9.4 Status of the deterioration and protection of Orange-Senqu sources (sponges) |  | FGEF
| 2.1.13.1 |  |  | 5.9.4 Protection of Orange-Senqu River Water Sources "sponges" | FGEF | 1 | EUR | 67600 |  | x | x | x | x | x | [16 empty] | 100% complete.
| 2.1.14 | 0 | Investigation of the continuation of the Nossob sandstone aquifer from Namibia into Botswana |  | x | 3
| 2.1.15 | 0 | Employment of more approaches to determine groundwater recharge | (in addition to Chloride mass balance applied in previous study). | x | 3
Planning | 2.2.01 | 0 | 5.5 Decision support guidelines and knowledge management system for ground water drought management (SADC Water Division) |  | SADC
| 2.2.01.1 |  |  | 5.5 Decision support guidelines and knowledge management system for ground water drought management (SADC Water Division) | SADC | 1
| 2.2.02 | 0 | 5.9.5 Integrated Water Resources Quality Management Plan |  | EU-GTZ
| 2.2.02.1 |  |  | 3.3.3 Water resources quality monitoring framework/plan | EU | 1 | EUR | 54000 | [5 empty] | x | x | x | x | x | x | x | [10 empty] | 100% complete.
| 2.2.02.2 |  |  | 5.9.5 Assessment of requirements to carry out an Integrated Water Resources Quality Management Plan for the Orange-Senqu River | GTZ | 1 | EUR | 223208 | [8 empty] | x | x | x | x | x | x | x | [7 empty] | 15% complete.
| 2.2.03 | 0 | 6.1.1. Guidelines for water and benefit sharing |  | EU
| 2.2.03.1 |  |  | 6.1.1 Development of the principles for water and benefit sharing | EU | 1 | EUR | 10500 |  |  |  | x | x | x | x | x | x | x | x | [11 empty] | 100% complete.
| 2.2.04 | 0 | 6.1.3 Strategic Action Plan (SAP) |  | UNDPGEF
| 2.2.04.1 |  |  | 6.1.3 Development of SAP draft final - focus on environmental sustainability | UNDPGEF | 2 | USD | 170000 | [22 empty] | Still coming. To be commenced in Q2 of 2010.
| 2.2.05 | 0 | 2.1.2 National Action Plans (NAPs) for IWRM implementation |  | UNDPGEF
| 2.2.05.1 |  |  | 2.1.2 Formulation of NAPs | UNDPGEF | 2 | USD | 250000 | [15 empty] | x | x | x
| 2.2.06 | 0 | 3.1.4 An Integrated Orange-Senqu River Basin Model accessible to all basin states |  | GTZ
| 2.2.06.1 |  |  | 3.1.4 Development of an Integrated Orange-Senqu River Basin Model accessible to all basin states | GTZ | 1 | EUR | 160533 | [9 empty] | x | x | x | x | x | x | [7 empty] | 10% complete
| 2.2.07 | 0 | 6.1 Basin-wide IWRM Plan |  | GTZ
| 2.2.07.1 |  |  | 6.1.4 Development of basin wide IWRM plan | GTZ | 1 | EUR | 400000 | [15 empty] | x | x | x | x |  |  |  | To be implemented under phase III in Q2 of 2011.
| 2.2.08 | 0 | 6.1.5 Donor Conference on the basin wide IWRM Plan |  | GTZ-UNDPGEF
| 2.2.08.1 |  |  | 6.1.5 Donor Conference on the basin wide IWRM Plan | GTZ | 1 | EUR | 25000 | [19 empty] | x
| 2.2.08.2 |  |  | 6.1.5 Donor Conference on the basin wide IWRM Plan | UNDPGEF | 2 | USD | 100000 | [19 empty] | x
| 2.2.09 | 0 | South Africa: Dual reticulation system guidelines for Gauteng (promotion of marginal water use) |  |  | 3
| 2.2.10 | 0 | Transboundary: Institutional, Policy, Legislative and Guidelines Review of the use marginal waters |  |  | 3
| 2.2.11 | 0 | Transboundary: Guidelines for marginal water use for the industrial sector |  |  | 3
Implementation | 2.3.01 | 0 | 5.1 Demonstration project on water conservation and quality control in the Irrigation sector |  | UNDPGEF
| 2.3.01.1 |  |  | 5.1.1 Water conservation and quality control in the irrigation sector - A demonstration project in lower Orange-Senqu (Outcomes contributing to 3.1.4) | UNDPGEF | 2 | USD | 900000 | [11 empty] | x | x | x | x | x | x | x | x | x | x | x | To be done in Q2, 2010.
| 2.3.02 | 0 | 5.7 Demonstration project on Environmental flows in Fish River and the Orange-Senqu Mouth |  | UNDPGEF
| 2.3.02.1 |  |  | 5.7.1bDemonstration project on Environmental flows in Fish River and the Orange-Senqu Mouth | UNDPGEF | 2 | USD | ? | [11 empty] | x | x | x | x | x | x | x
| 2.3.03 | 0 | 5.9.6 Demonstration project on community-led rangeland management |  | UNDPGEF
| 2.3.03.1 |  |  | 5.9.6 Improved land/range management | UNDPGEF | 2 | USD | 700000 | [11 empty] | x | x | x | x | x | x | x | x | x | x | x | To be commenced in Q2, 2010.
| 2.3.04 | 0 | Establishment of a Fund for Catchment Conservation |  |  | 3
| 2.3.05 | 0 | Implementation of an ORASECOM capacity building programme |  |  | 3
| 2.3.06 | 0 | Establishment of an integrated Molopo-Nossob Sub-Basin Groundwater Database |  |  | 3
| 2.3.07 | 0 | Lesotho: Irrigation of sport fields, the golf course and suitable food crops in Maseru with treated wastewater |  |  | 3
| 2.3.08 | 0 | Namibia: Irrigation of sport fields and suitable food crops in larger Namibian towns with treated waste water |  |  | 3
| 2.3.09 | 0 | Protection, rehabilitation and conservation of the Orange-Senqu sources (Sponges) |  |  | 3
| 2.3.10 | 0 | x
Monitoring | 2.4.01 | 0 | 3.1.2 GIS based information management system |  | UNDPGEF
| 2.4.01.1 |  |  | 3.1.2 Contributing to the establishment of functional GIS based information management system and website content | UNDPGEF | 2 | USD | 300000 | [11 empty] | x | x | x | x
| 2.4.02 | 0 | 3.3.1 Data acquisition and display system |  | GTZ
| 2.4.02.1 |  | 3.3 Design of a common basin observation and monitoring system | 3.3.1 Data acquisition and display system for the Orange-Senqu River System | GTZ | 1 | EUR | 130000 | [8 empty] | x | x | x | x | x | [9 empty] | 10% complete
| 2.4.03 | 0 | Joint Basin Survey on Water Resources Quality |  | MS, GTZ, EU, UNDP-GEF, LHDA |  |  | 125
| 2.4.04 | 0 | Aquatic Ecosystem Health Monitoring |  | EU |  | EUR | 10000 | [7 empty] | x | x | x
| 2.4.05 | 0 | Extension of ground water monitoring to remote areas in the Molopo-Nossob Sub Basin and capturing of natural changes |  |  | 3
| 2.4.06 | 0 | Monitoring of changes in ongoing groundwater table lowering |  |  | 3
| 2.4.07 | 0 | x
| 2.4.08 | 0 | x
| 2.4.09 | 0 | x
| 2.4.10 | 0 | x
| 3.1.01 | 0 | 1.1 Review of Legal issues |  | EU
Institutional | 3.1.01.1 |  |  | 1.1.1 Identification of potential legal constraints and opportunities for implementing recommendations | EU | 1 | EUR | 66200 |  |  |  |  | x | x | x | x | x | x | x | [11 empty] | 100% complete.
| 3.1.02 | 0 | 1.2.1 Review of ORASECOM roles, responsibilities, mandates and operational procedures |  | EU
| 3.1.02.1 |  |  | 1.2.1 Identification of roles, responsibilities, mandates and operational procedures of ORASECOM Institutions (linked to 1.5.2) | EU | 1 | EUR | 200000 |  |  |  | x | x | x | x | x | x | x | x | x | x | x | [8 empty] | Ongoing. 50% complete.
| 3.1.02.2 |  | 1.5 Institutional analysis on relation with bilaterals | 1.5.2 Relationship with bilaterals (linked to 1.2.1) | EU | 1 | EUR | 29300 | [22 empty] | Ongoing.
| 3.1.03 | 0 | 6.1.2 Review of basin-wide institutional issues |  | EU
| 3.1.03.1 |  |  | 6.1.2 Identification of key basin-wide water resources and institutional issues | EU | 1 | EUR | 72400 | [6 empty] | x | x | x | x | x | [11 empty] | 100% complete.
| 3.1.04 | 0 | 1.2.2 Review of international best practices for transboundary water management |  | EU
| 3.1.04.1 |  |  | 1.2.2 Investigation of international best practices for transboundary water management | EU | 1 | EUR | 96200 |  |  | x | x | x | x | x | x | x | x | x | x | [10 empty] | Ongoing.
| 3.1.05 | 0 | 1.9 Transboundary EIA Procedures |  | UNDPGEF
| 3.1.05.1 |  |  | 1.9 Development of EIA procedures in a transboundary context | UNDPGEF | 3 | USD | 100000 | [11 empty] | x | x | x | x | x | x | x | x | x |  |  | To be started in Q2, 2010.
| 3.1.06 | 0 | 2.1.1 Agreement and financial arrangements for NAP development |  | UNDPGEF
| 3.1.06.1 |  |  | 2.1.1Strengthening of institutions for NAP development | UNDPGEF | 3 | USD | 80000 | [11 empty] | x
| 3.1.07 | 0 | x
| 3.1.08 | 0 | x
| 3.1.09 | 0 | x
| 3.1.10 | 0 | x
Organisational | 3.2.01 | 0 | 2.3.1 RBO exchange programme |  | GTZ
| 3.2.01.1 |  | 2.3 International Congress on Basin Commissions, lessons learnt and secondments | 2.3.1 RBO exchange programme within SADC Region, Africa, and beyond, e.g. ICPDR | GTZ | 1 | EUR | 200000 |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | Ongoing. Cooperation with ICPDR exists.
| 3.2.02 | 0 | x
| 3.2.03 | 0 | x
| 3.2.04 | 0 | x
| 3.2.05 | 0 | x
| 3.2.06 | 0 | x
| 3.2.07 | 0 | x
| 3.2.08 | 0 | x
| 3.2.09 | 0 | x
| 3.2.10 | 0 | x
Individual | 3.3.01 | 0 | 2.2.1 Needs Assessment and Capacity Building Programme |  | EU-FGEF
| 3.3.01.1 |  | 2.2 Capacity building for technical staff and water resources practitioners in IWRM | 2.2.1 Needs assessment and capacity building programme formulation | FGEF | 1 | EUR | 118800 |  |  |  |  | x | x | x | x | [14 empty] | 100% complete.
| 3.3.01.2 |  |  | 2.2.1a Review/inputs to Needs Assessment work (2.2.1) | EU | 1 | EUR | 28000 |  |  |  |  | x | x | x | [15 empty] | 100% complete.
| 3.3.02 | 0 | 2.2.2 Training course on International Water Law |  | EU-FGEF
| 3.3.02.1 |  |  | 2.2.2 Delivery of module identified in assessment | EU-FGEF | 1 | EUR | 40000 | [7 empty] | x | [14 empty] | 100% complete.
| 3.3.03 | 0 | 2.2.3 Training course on Integrated Orange-Senqu Basin Model |  | GTZ
| 3.3.03.1 |  |  | 2.2.3 Capacity building on decision support models and systems and maintenance for managers and decision makers | GTZ | 1 | EUR | 40000 | [12 empty] | x | x | [8 empty] | 5% complete
| 3.3.04 | 0 | 2.2.4 Training course on SADC Treaties and UN Conventions |  | EU
| 3.3.04.1 |  |  | 2.2.4 Training course on IWRM and institutional issues | EU | 1 | EUR | 285000 | [22 empty] | 80% complete. One more training course to be identified within next PE.
| 3.3.05 | 0 | 2.2.4 Training course on Negotiation skills and conflict management |  | EU
| 3.3.05.1 |  |  | 2.2.4 Training course on Negotiation skills and conflict management | EU | 1 | EUR | [23 empty] | Specify the training courses
| 3.3.06 | 0 | 2.2.5 Training course on Transboundary Water Resources Management |  | UNDPGEF
| 3.3.06.1 |  |  | 2.2.5 Training course on water resources management - content to be defined (Timing: following 2.2.1) | UNDPGEF | 3 | USD | 180000 | [11 empty] | x | x | x | x | x | x | x | x | x | x
| 3.3.07 | 0 | Scholarship Programme |  | ICPDR
| 3.3.08 | 0 | Botswana: Awareness campaign to promote indirect potable water reuse and irrigation of food crops with treated sewage effluent |  |  | 3
| 3.3.09 | 0 | x
| 3.3.10 | 0 | x
Legend
[5 empty] | 1 | 1 | Funding secured and activity completed
[5 empty] | 2 | 2 | Funding secured and activity ongoing
[5 empty] | 3 | 3 | Funding pending
[5 empty] | 4 | 4 | Funding pending but under negotiation
Note on E121: pqwist: check with project manager
Note on AF6: • Procurement of office space is expected to be finalised by April 09. • Funding of office refurbishment and purchase of office furniture will now be jointly shared by all the ICPs and ORASECOM.
Note on AF8: • Procedures to be approved by Council in April 10. • Systems to be developed later.
Note on AF17: ● Total money spent is €89,170.00
Note on AF22: • New date of commencement of this activity and others under this project phase is Q2, 2010. • More intersectoral dialogue will be promoted. • Actual institutional setting to be established will be guided by ORASECOM.
Note on AF24: • Final report uploaded onto ORASECOM website • GTZ will organise a meeting for both EU and GTZ teams to establish linkages and harmonise their work on this issue of stakeholder participation.
Note on AF40: • The website was officially launched in October 09.
Note on AF43: • Orange-Senqu River Awareness Kit (RAK) was launched by ORASECOM on the 19th of October 2009, in Maseru, Lesotho
Note on AF47: • A pool of interactive PowerPoint slides have been developed for commissioners or members of parliament to use as and when required. • A 10-15 minutes video on the importance of the ORANGE-Senqu River as a transboundary river basin has been completed.
Note on AF52: • ORASECOM's intention with these materials may need to be clarified further. • Some of the intention could be to promote ORASECOM as well as projects. • The project will establish existing materials and develop missing materials. • Materials that will be developed will include foldable posters that can be displayed at international events. • There is a need to standardise the format of display of these materials or docs. • This is being undertaken by the EU team. • Currently, there are flyers produced under the GTZ (BMZ/DFID) Phase I Project Support. • Materials will be provided to member States for their use as well. • UNDP-GEF and EU will share the cost of production of these materials.
Note on AF53: • ORASECOM's intention with these materials may need to be clarified further. • Some of the intention could be to promote ORASECOM as well as projects. • The project will establish existing materials and develop missing materials. • Materials that will be developed will include foldable posters that can be displayed at international events. • There is a need to standardise the format of display of these materials or docs. • This is being undertaken by the EU team. • Currently, there are flyers produced under the GTZ (BMZ/DFID) Phase I Project Support. • Materials will be provided to member States for their use as well. • UNDP-GEF and EU will share the cost of production of these materials.
Note on AF55: • Exhibits have been presented at the Africa Water Week and the Orange River Symposium organised by the University of the Orange Free State (UOVS) in Bloemfontein. • Exhibit is planned at the Botswana Water Week.
Note on AF56: • ORASECOM participated in 5th GEF Biennial International Waters Conference from 26-29 October 2009 in Cairns, Australia
Note on AF58: • Methodologies for undertaking this work has been completed. • A comprehensive environmental and water quality survey is proposed for September/October 2010. • This survey will include information on the river biology, chemistry, aquatic health, and POPs. • This activity will be linked with sub-activity 4.4.
Note on AF61: • Final report uploaded onto ORASECOM website
Note on AF67: • Work on this work package is well underway. • As part of ensuring sustainability in the future, there is a significant capacity building component and a draft programme has been finalised after discussion with each of the riparian states. • Work will be completed by November 2010 and will include the extension and updating of the hydrology of many parts of the basin which have been neglected in the past. • Work on the Vaal Catchment and the Upper Orange has started and will be complete by end July 2010.
Note on AF71: • This is work package 6 • Good progress has been made in the assessment of the role of regulatory, economic, legal instruments can play as well in an assessment of current water demand management practices both locally and worldwide. • A major effort has been made to investigate the use of remote sensing in the setting up of an irrigation GIS/Database and a detailed methodology has been finalised. • Work on populating the GIS database is underway and comprises a combination of remote sensing and fieldwork. • The work will be completed in December 2010.
Note on AF74: • This is work package 4. • Assessment of the impact of global climate change on the hydro climatology, water resources, vulnerabilities and adaptation requirements in the Orange-Senqu Basin is being undertaken. • The majority of the work is being carried out by the Potsdam Institute for Climate Impact Research in Germany. • Work on data collection is underway and will be followed by the regional downscaling of a selected Global Climate Model. • Both statistical and dynamic downscaling methods will be applied. • This is a major and time-consuming activity and is only expected to be completed by September 2010. • The remaining work will be completed by November 2010.
Note on AF80: • Total money spent = €213,077.00.
Note on AF82: • The project has been completed. • Total money spent = €189,950.00. • Outcomes of this project may assist in informing a groundwater project being undertaken by Namibia in the Stampriet area. • Work being done by this project may need to be captured in future under the Gantt chart as well. • More projects on groundwater are recommended.
Note on AF84: • This is work package 5. • This is the largest of the work packages and includes a number of objectives, the most important of which are: • A basin-wide scoping level assessment of ecological and socio- cultural condition and importance • Delineation of management units and selection of EFR sites • Biophysical and hydraulic surveys • Assessment of present ecological state • Assessment of flow requirements and ecosystem services • A considerable amount of progress has been made as indicated by the completion of several deliverables including the design of the stakeholder process, a gap analysis of EFR studies and the establishment of a number of databases and models. • Work is on schedule and will be completed by December 2010.
Note on AF86: • The project will commence in Q2 of 2010. • This project will look at broader aspects such as broader environmental requirements rather than specific flow requirements. • The inception of the project will ensure synergies with other projects e.g. GTZ (BMZ/DFID) phase II project. • The project implementation will be tendered out to a consortium of consulting companies with TORs. • Need for avoidance of overlaps will be included in the TORs.
Note on AF88: • Total money spent is €77,918.00.
Note on AF90: • The project will commence in Q2 of 2010. • This will be linked with activity 4.3.1. • Detailed planning will be done
Note on AF92: • Study area still needs to be identified by Council.
Note on AF96: • The project has been completed. • Total money spent = €119,900.00. • The final project report has to be included in the Gantt chart as per the ORASECOM Council resolution.
Note on AF102: • Final report uploaded onto ORASECOM website
Note on AF103: • Good progress has been made and the team is collaborating closely with the EU support project in establishing a water quality monitoring framework acceptable to the basin states. • A second workshop on this and other aspects took place on 2 March 2010 in order to confirm the framework. • With the confirmation of this framework, the main work of detailing monitoring protocols and database systems will be developed. • Work will be completed in November 2010.
Note on AF105: • Draft principles are available for discussion, and will inform ongoing work on the institutional structures.
Note on AF107: • The implementation of this project will be undertaken in Q2 of 2010. • An IWRM Plan will be a consolidation of all the studies and plans that will be in place by 2012 including environmental plans such as SAPs. • Linkages between e.g. NAP and IWRMP need to be discussed.
Note on AF111: • Work resumed in September 09 as Work Package 1 of IWRM Phase 2 • Work on this work package is in its preparatory phase and depends to a large extent on the work being carried out in Work Package 2, the updating and extension of the hydrology. • Work currently being carried out includes an assessment of model strength and weaknesses, definition of the capacity- building component and the incorporation of the (updated) Lesotho Lowlands System into the overall system. • Work will be completed in January 2011 r
Note on AF113: • This project will be implemented under phase III of the GTZ (BMZ/DFID) support starting from Q2 of 2011. • Review process of how this activity and Phase III of the GTZ(BMZ/DFID) work will be achieved will be done in 2010.
Note on AF125: • The project implementation will commence in Q2 of 2010. • This project needs to be harmonised with the Sponges Project that was funded by FGEF, as well as the Lesotho national project on sustainable land management being funded by UNPD. • A mission comprising UNDP-GEF & Secretariat was undertaken to establish synergies with Lesotho project mentioned above on 27 January 2010.
Note on AF136: • Work Package 2 inlcudes a review of the data acquisition systems at the national and HYCOS levels for hydrological data. • Proposals will be made for a data (acquistion) display system for the Orange-Senqu River System largely based on the data acquired at the national level. • Submission of this proposal is planned for Nov 2010
Note on AF146: • Final report uploaded onto ORASECOM website.
Note on AF148: • Work has been extended on recommendation from Council • A series of delphi workshops are planned for 2010.
Note on AF149: • Being addressed under institutional work (act 1.2.1).
Note on AF151: • Draft principles are available for discussion, and will inform ongoing work on the institutional structures.
Note on AF153: • Team visited ICPDR on 12-17 July 09. • Other trips e.g. to Nile - Senegal or Volta are planned.
Note on AF163: • ICPDR was visited in July 08 by ORASECOM and OKACOM Commissioners. • ORASECOM Secretariat Participated in the the Preparations and the 12th Ordinary Meeting of the ICPDR held in Vienna, 10-11 Dec 2010. • MoU is being developed between ORASECOM and ICPDR. • Other RBOs will be visited. • ES represented ORASECOM at the 2009 World Water Week.
Note on AF174: ● Total money spent is €76,447.00.
Note on AF177: • Total money spent from (i) FGEF = € 20,000.00 and (ii) EU = €20,000.00. • More courses recommended.
Note on AF179: • This is work package 2. • Preparatory work has been completed. • The development of an integrated Orange-Senqu River Basin model will be rendered accessible to all basin states through a capacity-building module. • Capacity-building will be provided during November 2010, once the model has been extended and updated to cover the whole basin. • The capacity-building will comprise a short (1 day) course for ORASECOM delegates and other senior decision-makers and a longer (minimum 1 week) course for water resources practitioners. • Capacity building will take place both in each basin state and at a central training venue in South Africa.
Note on AF181: • Training courses delivered on following: International Water Law, SADC Treaties, and Negotiation Skills and Conflict Mngt.
Overview

## Funding Overview
Funding Overview
Sum of Amount | Column Labels
Row Labels | EUR | USD | ZAR
EU | 2170400
EU-FGEF | 40000
FGEF | 681700
GTZ | 3422224
ICPDR | 2000
ORASECOM |  |  | 10000000
UNDPGEF |  | 5700000
Grand Total | 6316324 | 5700000 | 10000000

## Terminology
Terminology
Governance | The manner in which authority is acquired and exercised on behalf of the public in developing, utilizing, and protecting water resources
Management | The activity of planning, organizing, staffing, directing, and controlling an organization for the purpose of accomplishing a goal.
Participation | The process of involving stakeholders in problem solving or decision-making and using the stakeholders input to make better decisions. A stakeholder is an individual, group or institution that has a defined and recognized interest in a decision making process or project.
Communication | The activity of conveying information in an attempt to create a common understanding among all stakeholders.
IWRM/TWM | The technical activities of planning, developing, distributing and optimizing the use of water resources under defined water polices and regulations
Assessment | The process of involving stakeholders in problem solving or decision-making and using the stakeholders input to make better decisions. A stakeholder is an individual, group or institution that has a defined and recognized interest in a decision making process
Planning
Implementation
Monitoring
Capacity Development | A comprehensive process that aims at strengthening the abilities of peoples and societies to perform functions, solve problems, and achieve objectives in a sustainable manner.
Institutional | Overall system of rules and regulations.
Organisational | Formally-organized structures
Individual | Human resources
Overview

## About
About
The Monitoring and Budget Planning System for the Orange-Senqu River Commission has been developed in close collaboration between the ORASECOM Secretariat and Transboundary Water Management (TWM) Programme in SADC.
The TWM Programme in SADC in funded by the German and UK Governments
In Delegated Cooperation with:
Commissioned by: